## Function List
Document Management System (Step 1)
Funtion List
80%
No | Module & Function Name |  | ManDays | Man Power | Schedule (days) * 70% MP allocated | Total (Mandays) | Total Days Allocated | Total Month
1 | Document Management |  | 24 | 5 | 30 | 49 | 48.75 | 2.2159
| 1.1 | Document Show and Searching | 5 | 1 | 6.25
| 1.2 | Add Document | 5 | 1 | 6.25
| 1.3 | Document Details | 6 | 1 | 7.5
| 1.4 | Document Preview | 3 | 1 | 3.75
| 1.5 | Version Control | 5 | 1 | 6.25
2 | Security |  | 8 | 1 | 10
| 2.1 | Users and Role | 8 | 1 | 10
3 | Administration |  | 17 | 1 | 8.75
| 3.1 | Dashboard | 7 | 1 | 8.75
| 3.2 | Master Division | 5 | 1 | 6.25
| 3.3 | Master Department | 5 | 1 | 6.25

## Schedule
Schedule
Maintenance Management System
No | Item |  |  |  | Sept'24 |  |  | Oct'24 |  |  |  |  | Nov'24 |  |  |  | Dec'24 |  |  |  | Jan'25 |  |  |  |  | Total Days |  | Progress (%)
[5 empty] | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | 70 |  | 50%
[5 empty] | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  |  |  |  | 35
[5 empty] | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 |  |  |  |  | 175
| Total Working Day |  |  |  | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 5 | 5
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -5 | Plan |  | Actual |  | 23.78%
1. | UR |  | 5 | 0 | Sept'24 W2 9 13: 5 | 5 | 7.143% | 5 | 7.143%
2. | SD |  | 19 | 0 | Sept'24 W3 16 20: 4; Sept'24 W4 23 27: 5; Oct'24 W1 30 4: 5; Oct'24 W2 7 11: 5 | 19 | 27.14% | 19 | 27.14% | 49
3. | Programming |  | 45 | 0 | [21 empty] | 45 | 64.29% |  | 0% | 104
| Document Management |  | 24 | 0 | [22 empty] | 34.29%
| 1.1 | Document Show and Searching | 5 | 0 | Oct'24 W3 14 18: 5 | 5 | 7.143% | 5 | 7.143%
| 1.2 | Add Document | 5 | 0 | Oct'24 W4 21 25: 5 | 5 | 7.143% | 1 | 1.429%
| 1.3 | Document Details | 6 | 0 | Oct'24 W5 28 1: 5; Nov'24 W1 4 8: 1 | 6 | 8.571% | 5 | 7.143%
| 1.4 | Document Preview | 3 | 0 | Nov'24 W1 4 8: 3 | 3 | 4.286%
| 1.5 | Version Control | 5 | 0 | Nov'24 W1 4 8: 1; Nov'24 W2 11 15: 4 | 5 | 7.143% |  | 0%
| Security |  | 8 | 0 | [21 empty] | 8 | 11.43% |  | 0
| 2.1 | Users and Role | 8 | 0 | Nov'24 W2 11 15: 1; Nov'24 W3 18 22: 5; Nov'24 W4 25 29: 2 | 8 | 11.43% |  | 0%
| Administration |  | 13 | 0
| 3.1 | Dashboard | 7 | 0 | Nov'24 W4 25 29: 2; Dec'24 W1 2 6: 5
| 3.2 | Master Division | 3 | 0 | Dec'24 W2 9 13: 3
| 3.3 | Master Department | 3 | 0 | Dec'24 W2 9 13: 2; Dec'24 W3 16 20: 1 | 7 | 10% |  | 0%
4. | ST |  | 4 | 0 | Dec'24 W3 16 20: 4 | 4 | 5.714% |  | 0%
5. | UT |  | 20 | 0 | Dec'24 W4 23 27: 4; Jan'25 W1 30 3: 4; Jan'25 W2 6 10: 5; Jan'25 W3 13 17: 5; Jan'25 W4 20 24: 2 | 20 | 28.57% |  | 0%
6. | Go Live |  | 1 | 0 | [21 empty] | 1 | 1.429% |  | 0% | bar: Jan'25 W4 20 24